## Task List
Activity | Description | Comments | Responsibility | Begin Date | Close Date | Current Status
Project Idea & Proposal | Drafting of the project idea and submitting it to the Hackathon organizers | Completed | Andrew |  |  | Complete
Requirements Specification | Gathering, discussing & drafting of system specifications and user requirements. | Completed | Andrew & Jonathan |  |  | Complete
System Design | Designing System Use Case | Completed | Jonathan |  |  | Complete
| Designing the Data Model | Completed | Jonathan |  |  | Complete
Database design | Developing the system database | Completed Database is open to minimal changes during development | Jonathan |  |  | Complete
Location Management module | Districts Addition form & DB insert | To add district with it's respective geographical cordinates | Jonathan
| County Addition form & DB insert | To add county with it's respective geographical cordinates plus district it belongs to | Jonathan
| Sub-county Addition form & DB insert | To add sub-county with it's respective geographical cordinates plus county it belongs to | Jonathan
| Parish Addition form & DB insert | To add parish with it's respective geographical cordinates plus sub-county it belongs to | Jonathan
| Village Addition form & DB insert | To add village with it's respective geographical cordinates plus parish it belongs to | Jonathan
User Management Module | Admin Login Page & Login Script | Page for admin to login | Jonathan
| Agents Registration Form & Database update | Form to add an agent and assign him/her to a location | Jonathan
| Agents Registration Email Notification | Email notification to the agent upon registration | Jonathan
| Registered agents display page in admin panel | Code availabe, only required to edit variables | Jonathan
| Registered agents deletion form & database update | Code availabe, only required to edit variables | Jonathan
Agents Profile Management | Agents Login Page & login script |  | Evelyn
Market Information Management Module | Market registration form & Database update | Adding a market, assign it to the location in which the agent operates and register its geographical coordinates | Evelyn
| Market Prices From & DB Insert | Adding a market commodity, assigning it to markets where it is sold and the price at which it is sold | Evelyn
House Hold Agricultural Information Management | Household Information addition form & DB insert | Add household details, geographical location coordinates and assigning them to the location in which the agent operates | Evelyn
| Household crop information addition form & DB insert |  | Evelyn
| Household livestock information addition form and DB insert |  | Evelyn
| Household livestock products information addition form and DB insert |  | Evelyn
| Household farming tools & suppliments addition form & DB insert | Form for adding agricultural suppliments and farming tools used by the household | Evelyn
| Household challenges & abnormalities information addition form & DB insert |  | Evelyn
Weather Information Management module | PHP API that picks live weather information from the open weather map API and periodically updates it in the system database | Not Started | Evelyn